SUPPORTING INFORMATION – HATFIELD & STAINFORTH DIVERSIONS AND FACTORS AFFECTING SERVICES

Current revised train times during the Hatfield & Stainforth disruption

First TransPennine Express services to Cleethorpes – replaced by buses between Doncaster and Scunthorpe.

First Hull trains running via Selby as usual

Northern Rail services between Leeds & Goole via Knottingley operating as normal.

Northern Rail services between Doncaster and Hull are diverted via Selby.  Buses will serve intermediate stations between Doncaster and Goole. Train services are operating  between Goole and Hull

Northern Rail services to Scunthorpe are replaced with buses between Doncaster and Scunthorpe.

Northern Rail services between Sheffield and Cleethorpes via Brigg which operate on Saturdays only are running as normal.

Freight services – approximately 150 services per day being diverted via a circular route over the Brigg Lincoln lines.

Proposed improvements to services above

The Brigg line is already highly congested because of the disruption but potential plans for a limited weekend service operated by First TransPennine Express are being explored. Further details of such will be released as and when plans are confirmed.

Nottingham resignalling

A critical date for the rail network is 20 July when 37 days of vital works are begin at Nottingham station.  Although this is many miles from the site of the slip it will restrict the flow of freight services even further.  These trains are carrying oil (including aviation fuel for airports); coal to power stations at Rugeley and Ratcliffe; and steel coils.  Because of the spoil slip, steel trains from Immingham to South Wales for production processes and to provide materials for Network Rail’s own renewals are also going through Nottingham. All of these flows are essential to support the UK economy and electricity generation.

The Nottingham work is vital as it replaces life-expired signalling, improves capacity for future service enhancements, and enables improvements to station facilities.  The work was originally planned for summer 2012 but postponed to allow services to run for the Olympics.  To reschedule this work would not only be very be costly but would reduce the reliability of the network in the long term.  Every effort is being made to complete the repair at Hatfield & Stainforth before these works but this may not be possible.  Planning teams are working urgently to develop a revised timetable which can accommodate the diversions caused by the Hatfield Colliery slip and the Nottingham blockade.

Selby swing bridge

Selby Swing bridge is due for renewal this summer (28 July to 9 September). These works will see life-expired steel members being replaced and strengthened, full reconstruction of the road bridge, track and rail bearer replacement along with a full grit blast and painting of the structure. Network Rail teams are currently planning that this will go ahead.

Hull will remain connected to the main rail network.  First Hull Trains and Northern Rail are working with Network Rail to establish an alternative diversionary route to make sure that Hull remains connected with Doncaster and onward routes. Details will be published as soon as they are available.

The following travel arrangements are already in place:

- First TransPennine Express (normally 15 services per day between Manchester and Hull) Manchester services terminate at Selby with both stopping and express buses running to Hull

- Northern Rail: (normally 24 services per day) Train services are running to Selby with a bus replacement service between Selby and Howden and a train service between Howden and Hull. An express bus service will also operate between Hull and York direct.

- Freight (approx 8-10 services per day) to/from Hull Docks will operate via Snaith

- East Coast (one train per day). Was to divert along the route which is unavailable because of the landslip.  Decision about services under consideration.

Hull – bridge works in August

In addition to the work at Selby, there are three bridge reconstructions and a bridge waybeam replacement scheme that are planned on the route to Hull which will additionally affect trains.  These are:

Friday night (16 August) James Reckitt Avenue – bridge reconstruction.

Full bridge reconstructions over the August bank holiday (24 August):

Market Weighton Canal - Bridge reconstruction with a 1000t crane - 54hrs
Spring Bank West - 32m long full bridge reconstruction being drive in with the aid of a self propelled modular transporter.  This reconstruction will prevent pedestrian and vehicular access down this main road to the Hull City stadium.

Waybeam Replacement: Dairycoates intersection bridge – 77 hours

Brigg Line

The Brigg Line is currently experiencing a considerable increase in the number of trains per day and associated tonnage this involves. Maintenance teams are working intensively on Saturday night / Sunday mornings in order to maintain track standards.  Some additional maintenance access may also be necessary to counter the impact the additional traffic is having on the route.  This is being carefully planned and managed in order to minimise disruption but also maintain safe track standards. The need to safely complete this work restricts the number of services which can be accommodated on the Brigg line.

Passenger services on Brigg line

Northern Rail operates three return services between Sheffield and Cleethorpes each Saturday over the Brigg Line.  Part of the reason that operators trains are unable to operate additional passenger services on this route is that First TransPennine Express train crew do not currently know this route. The necessary safety standards for competent drivers requires in depth knowledge of the track, the signals on the route and specific locations. Whilst a process of route learning is underway, this is a slow and timely exercise with each individual crew member requiring six days of route learning training. The drivers who normally operate between Scunthorpe and Doncaster also operate on different routes and therefore releasing sufficient numbers for training is a time consuming task. 
This is in addition to the limited opportunities offered by the fact that the Brigg line is currently being heavily used by diverted essential freight services.